DEBO RISE

First Pilot: Complete 6-Week Plan (Version 2)

Rise together.   Web Development | Video Editing | Financial Markets (Forex) Basics

Prepared by: Besukal Gobena, Program Lead      For: School Principal, Mentors, and Partners

Debo Rise is a free 6-week program for Fit Awrari Abayneh Secondary School students. Students choose one field, learn from simple lessons, build one real project, and finish with a school-authorized certificate. Every lesson has one idea, one task, and a clear “done when” check. The pilot runs outside class hours with a teacher supervising every group. Grades come first.

# 1. The Pilot at a Glance

| Item | Plan |
| --- | --- |
| Program | Debo Rise, first pilot (a small, safe test before anything bigger). |
| Duration | 6 weeks of learning, plus about 10 days of pre-launch (announce, apply, select, onboard). |
| Fields | Web Development (HTML and CSS only), Video Editing, and Financial Markets Basics (forex education only). |
| Group size | 24 to 30 students (about 8 to 10 per field), plus a waitlist of about 5. |
| Time | 1 to 2 hours every day (Day 7 is rest) and 2 meetings a week. |
| Meetings | Meeting A: in person at school, 60 minutes. Meeting B: online, 45 minutes. |
| Method | Learn, Think, Build, Solve, Teach. |
| Lessons | Short videos (10 to 30 minutes), a task for every lesson, and written notes. |
| Daily proof | Students post proof of work (screenshot, photo, or short note) in their field group. |
| Final projects | Web: a responsive website for one real business. Video: a short promo video for a real client (to be confirmed with the video partner). Financial Markets Basics (forex education): a Starter Report with a paper-trading journal (no real money). |
| Certificate | Authorized by the school and Debo Rise. Earned by finishing the project. |
| Ending | Showcase Day at school for the principal, teachers, parents, and mentors. |
| Success targets | At least 20 students join. 70% or more attend regularly. At least 60% finish a project. At least 5 written testimonials. |

# 2. Who Does What

| Person | Responsibilities | Deadline |
| --- | --- | --- |
| Program lead (Besukal) | Runs the program, teaches Web Development, runs the Google Form and tracker, leads Meetings A and B, reviews all lessons, writes the final report. | Ongoing |
| Video editing partner | Builds the video course with the lead: lessons, practice footage, tool choice, final project. Gives feedback on student work. | Course ready for Week 1 by Day -3 |
| Forex mentor | Prepares about 30 short video lessons (5 per week for 6 weeks) matching the course map, plus a 1-page note per week. Answers student questions in the group by text or short voice note. Follows the Mentor Agreement (a separate one-page agreement). | Weeks 1 and 2 videos by Day -3. Then 1 week ahead, every week. |
| Supporter students (2 or 3) | Take attendance, send reminders, host meetings with the teacher, help at Showcase Day, check on quiet students in a friendly way. | Briefed by Day -1 |
| Guest speaker (optional) | One online session in Week 5 on digital marketing and sharing your work (30 to 45 minutes), for all fields. | Date set by Day -5 |
| Principal (school director) | Approves the pilot, the three fields, the parent note, and the certificate. Attends Showcase Day. | At this meeting (Section 11) |

# 3. Keeping Students Safe: Mentor Rules

| Rule | What it means |
| --- | --- |
| If a student writes privately | The mentor does reply in private. But They also send the student back to the group and tell the lead or the teacher. |
| Forex is education only | Teach: money, exchange rates, how to read charts, risk, and scams. Practice only on past charts in a journal. No real money. No broker or trading accounts. No live signals. No profit promises or screenshots of profits. No recommending apps or brokers. |
| No selling to students | No promotion of paid mentorships, courses, or groups to students during the program. Any offer after the program goes only to parents, and only with the principal’s written permission. |
| Content is checked first | The lead and the supervising teacher watch every video before students see it. Videos must be in simple English or Amharic, 10 to 30 minutes, and match the course map. |
| A teacher is in every group | The supervising teacher can see all messages and can remove anyone who breaks the rules. |

# 4. How We Keep Every Lesson Simple

Students who want to learn told us two things: clear sections, and small steps they can finish. These rules apply to every course.

| Rule | What it looks like |
| --- | --- |
| One lesson, one idea | A lesson teaches only one thing. Videos are 10 to 30 minutes at most. |
| Plain words | Use simple English and Amharic. If a student meets a new word, they can ask and it is explained. |
| Same layout every day | Read the task, Watch the lesson, Do the task, Post proof. |
| One task, one check | Each lesson ends with a small task. Each week ends with one deliverable and a “you are done when” check. |
| Small wins | Weekly progress sheet (one page for each student). Shout-outs for the best help and the best progress. |
| Never stuck alone | Post #CallADebo if you are stuck for 20 minutes. Classmates and mentors gather to help, like a debo in a village. |
| Buddy system | Each student has a buddy to check in with during the week. |

# 5. How the Six Weeks Work

| Week | Phase | Main question | Result |
| --- | --- | --- | --- |
| 1 | Learn | What is this skill and how does it work? | Basics and a first small task. |
| 2 | Think | Who is this for, and what problem am I solving? | A real client or problem. Also, more depth lessons. |
| 3 and 4 | Build | Can I make it real? | Week 3: first draft. Week 4: full draft. |
| 5 | Solve | Does it work for a real person? | Test, feedback, and improve. Final project. |
| 6 | Teach | Can I explain what I learned? | Teach-back and Showcase Day. |

Learning continues every week, with new lessons each day.

## The Weekly Rhythm

| Day | What happens |
| --- | --- |
| Day 1 | Meeting A, in person (60 min): weekly goal, discussion, demo, first task. |
| Days 2 and 3 | Daily work (1 to 2 hours). Post proof. |
| Day 4 | Meeting B, online (45 min): share progress, solve problems. |
| Day 5 | Daily work (1 to 2 hours). Post proof. |
| Day 6 | Finish and submit the weekly deliverable (about 1 hour). |
| Day 7 | Rest day. The lead and supporters review submissions and post a short summary. |

## The Daily Routine (1 to 2 hours)

| Time | Step | What to do |
| --- | --- | --- |
| 5 min | Read | Read today’s task in your group. |
| 30 to 45 min | Watch | Watch the lesson. Take notes. |
| 30 to 60 min | Do | Do the task. Make something, even if it is small. |
| 5 to 10 min | Post proof | Post a screenshot, photo, or short note with the day number. |

## Meeting Plans

| Meeting | Agenda |
| --- | --- |
| Meeting A (60 min, in person) | 5 min: welcome and wins. 10 min: discussion question. 30 min: lesson demo and practice. 10 min: weekly goal and tasks. 5 min: attendance. |
| Meeting B (45 min, online) | 5 min: check-in. 10 min: two or three students show their work. 20 min: #CallADebo problem solving. 5 min: plan for the next days. 5 min: attendance. |

Who leads:  Web: the lead (Besukal Gobena) with teacher Melkamu. Video: the video partner (Daniel Wendimu). Financial Markets (forex): a trained supporter (Yosef Girma), with the supervising teacher present, using the mentor’s videos.

Think questions for Meeting A: Week 1: What do I want to do in 6 weeks? Week 2: What makes something good for a real person? Week 3: What is hardest so far? Week 4: What would a user complain about? Week 5: What surprised me in the feedback? Week 6: What can I teach?

# 6. Final Projects, Scoring, and Certificate

| Field | Final project | Minimum to count as finished |
| --- | --- | --- |
| Web Development | Responsive website for one real business | Homepage with header and menu, hero, services or products, about, contact, and footer. Works on phone and computer. Tested on a phone. Feedback record. |
| Video Editing | Short promo video (to be confirmed) | 60 to 90 seconds, clear story, clean cuts, readable text, balanced sound, correct export format. Feedback record. |
| Financial Markets (forex) Basics | Starter Report | Glossary, Risk and Scam Checklist, trading plan, journal of 10 paper trades with review, 1-page note on how exchange rates affect a local business. A 3-minute talk. |

### Scoring (100 points, pass is 60)

| Category | Points | What mentors look for |
| --- | --- | --- |
| Project completed | 30 | All minimum parts are done and submitted on time. |
| Quality of work | 30 | Web: works on phone, clean structure. Video: pacing and sound. Financial Markets(forex): clear understanding, honest records, risk rules followed. |
| Real problem and feedback | 20 | Worked with a real person, got feedback, and showed what changed. |
| Presentation and teach-back | 10 | Clear, honest, and well prepared. |
| Participation | 10 | Attendance, daily proof, and helping others. |

### Certificate rules

| Requirement | Standard |
| --- | --- |
| Meetings | At least 9 of 12 meetings (75%) and Showcase Day. But based on their field. |
| Daily proof | At least 20 proof posts (the goal is 4 a week, about 24). |
| Project | Finish and submit the final project with a score of 60 or more. |
| Presentation | Present at Showcase Day. |
| Grace period | Students who are close get 7 extra days after Showcase Day. |

The certificate shows the student’s name, field, project title, the dates, the signatures of the school director and the program lead, the school stamp, and a certificate number (for example DR-P1-001). The Financial Markets certificate says it is an education course only and does not qualify anyone to trade.

# 7. Pre-Launch and the Application Form

| Day | Action | Owner | Done |
| --- | --- | --- | --- |
| Day -10 | Principal meeting and decisions (Section 11). Agree dates. Send the Mentor Agreement to the forex mentor. Meet the video partner to fix the final project and tool. | Lead, principal | ☐ |
| Day -9 | Build the Google Form and tracker. Finish the poster and announcement. Ask for the school announcement. | Lead, supporters | ☐ |
| Day -8 | Announce. Applications open. | Lead, supporters, teacher | ☐ |
| Day -6 | Info session and taster (60 minutes). For the forex taster, play a 5-minute sample video from the mentor. | Lead, partners | ☐ |
| Day -5 | Reminders and Q&A. Set the guest speaker date. | Supporters | ☐ |
| Day -4 | Applications close. Undecided students choose a field. | Lead | ☐ |
| Day -3 | Select students with the teacher. Weeks 1 and 2 forex and video lessons must arrive and be reviewed. Send the parent note. | Lead, teacher | ☐ |
| Day -2 | Create groups, add students, pin the rules, send the pre-survey. | Lead, supporters | ☐ |
| Day -1 | Final check: rooms, Week 1 lessons, attendance sheet, mentors reminded. | Lead | ☐ |
| Day 1 | Kickoff (Meeting A, in person). | Everyone | ☐ |

### Changes to the Google Form

- Field choices: Web Development / Video Editing / Financial Markets Basics (forex education) / Not sure yet. Remove Graphic Design.

- Add a required checkbox: “I understand Financial Markets Basics is education only. No real money and no trading accounts.”

- Add a required checkbox for the parent: “My parent or guardian knows about this field and agrees.”

- Keep the questions on time, device, internet, exams, parent contact, and photo and video permission.

- Update the description to list the three fields.

### Selection

Choose students who can attend both meetings, give about 1 hour or more daily, and have parent permission. Score the motivation answer from 1 to 5. Aim for 8 to 10 students per field and keep a waitlist of about 5. Beginners and undecided students are welcome.

# 8. Showcase Day (2 hours)

| Minutes | Part |
| --- | --- |
| 10 | Opening by the principal and the lead. |
| 30 | Stage presentations: 2 students per field, 4 minutes each, chosen by the scoring checklist. |
| 30 | Exhibition: every student has a station and explains their work in 2 minutes. |
| 10 | Comments from guests and mentors. |
| 25 | Certificate ceremony. |
| 5 | Closing and thanks. |
| 10 | Group photo (only with photo permission). |

Bring offline copies of every project, printed work, and a phone backup in case of power or internet problems. The forex mentor and video partner are invited. The forex mentor may join by a short -recorded message if he does not attend.

# 9. Tracking and the Final Report

| What | How | When |
| --- | --- | --- |
| Applications | Google Form and Sheet | Pre-launch |
| Attendance (12 meetings) | Attendance sheet kept by a supporter | Every meeting |
| Daily proof | Count from the groups | Weekly |
| Weekly deliverables | Submission folder and checklist | Weekly |
| Confidence survey (1 to 5) | Same 4 questions before and after | Day 1 and Week 6 |
| Final score | Scoring checklist | Weeks 5 and 6 |
| Testimonials | 3 questions to students, mentors, and teacher | Week 6 |

Survey questions: I can do the main skill of my field on my own. I can finish a real project. I know my next step. I feel confident presenting my work.

Early warning: if a student misses 2 meetings or posts no proof for 5 days, a supporter or the teacher follows up in a friendly way. Final report to the principal (1 to 2 pages): numbers, photos, confidence change, testimonials, lessons learned, and advice for the second group.

# 10. Risks and Backup Plans

| Risk | Backup plan |
| --- | --- |
| Mentor videos arrive late | Weeks 1 and 2 must be in by Day -3. If not, delay the field’s start by one week or use free lessons for that week. |
| Students want to trade real money | Remind them of the rules. Talk to the parents. Remove the student from the field if needed. |
| A mentor promotes a paid service to students | Stop it at once and inform the principal. The agreement allows offers to parents only, with written permission. |
| Parents or school worry about forex | Show Section 3 and explain the course. Offer to remove the field. Never start without the principal’s approval. |
| Fewer than 20 applicants | Extend the deadline by 2 days and invite students through teachers. A group of 15 is still a valid test. |
| Students drop out | Friendly follow-up. Fill early gaps from the waitlist in Week 1. |
| The lead workload | Supporters host meetings with the teacher. A developer friend reviews code. The lead’s exam days are protected. |
| No laptop or weak internet | Use the school computer room after class. Choose phone-friendly tasks. VS Code works offline. Allow a 1-day grace. |
| Broken or removed video links | Check links 2 days before each week and keep backup lessons. |
| Online safety problem, or a mentor contacts students privately | Teacher in every group and pinned rules. Remind the mentor of the agreement and tell the teacher and the principal. Remove the mentor if it happens again. Contact parents when needed. |

# 11. Decisions Needed from the Principal

| Decision | Yes | No |
| --- | --- | --- |
| Approve the 6-week pilot, outside class hours. | ☐ | ☐ |
| Approve the three fields: Web Development, Video Editing, and Financial Markets Basics (education only, with the rules in Section 3). | ☐ | ☐ |
| Allow a room for Meeting A each week, computer room time for students without laptops, and the hall for Showcase Day. | ☐ | ☐ |
| Allow the lead and the supervising teacher to review all mentor videos before students see them. | ☐ | ☐ |
| Approve the parent note and the photo and video permission. | ☐ | ☐ |
| Authorize a school-signed certificate. Signed by: ______________________ | ☐ | ☐ |

Start date: ____________     Showcase Day: ____________

### Questions the principal may ask

| Question | Answer |
| --- | --- |
| Why teach forex? | Students asked about it, and a mentor has prepared lessons. We teach money, risk, and scam awareness, which protect students. |
| Will students trade with real money? | No. Practice is on past charts in a journal. No trading accounts. No real money. |
| Can the mentor message students? | No. Answers are in the group, or through the Ask the Mentor form, with the teacher present. |
| Is it legal? | We teach ideas only and will confirm what is allowed before we start. |
| What does the school risk? | Little. It is small, free, supervised, and the school can stop it at any time. We can remove the forex field if you prefer. |

Date: ____________

Principal’s name and signature: __________________________

Program lead’s signature: _______________________________