DEBO RISE

First Pilot: Complete 6-Week Execution Plan

Rise together.   Graphic Design | Video Editing | Web Development

Prepared by: Besukal gobena, Program Lead      Version: 1.0

How to use this document Sections 1 to 4 explain the pilot, the team, and what is still open. Section 5 is the pre-launch plan (announce, select, onboard). Section 6 explains how the 6 weeks work. Section 7 is the week-by-week lesson plan for all three fields. Sections 8 to 12 cover learning content, scoring, the certificate, Showcase Day, tracking, and risks. Section 13 lists your next actions. Anything in [square brackets] must be filled in.

# 1. The Pilot at a Glance

| Item | Plan |
| --- | --- |
| Program | Debo Rise, first pilot (the analysis stage). A small, safe test before building anything bigger. |
| Duration | 6 weeks of learning, preceded by about 10 days of pre-launch (announce, apply, select, onboard). |
| Fields | Graphic Design, Video Editing, and Web Development (HTML and CSS only). |
| Group size | 24 to 30 students (about 8 to 10 per field), plus a waitlist of about 5. |
| Time commitment | 1 to 2 hours of work every day (Day 7 each week is a rest day) and 2 meetings per week. |
| Meetings | Meeting A: in person at school (60 min). Meeting B: online on Telegram or a video call (45 min). |
| Method | Learn, Think, Build, Solve, Teach. Each phase has its own week or weeks. |
| Learning material | Carefully chosen online lessons (links with exact timestamps), a worksheet for every lesson, and mentor sessions. |
| Daily proof | Every student posts proof of their daily work (screenshot, photo, or short note) in their field group. |
| Final projects | Web: a responsive website for one real business. Design: a mini brand kit for a real client. Video: a short promo video (to be confirmed with the video mentor). |
| Certificate | Authorized by the school and Debo Rise. Earned by finishing the project, not only by attending. |
| The ending | Showcase Day at school with the principal, teachers, parents, and mentors. |
| Pilot success targets | At least 20 students join. 70% or more attend regularly. At least 60% finish a project. At least 5 written testimonials. |

# 2. What Is Confirmed and What Is Still Open

### Confirmed

- Three fields: Graphic Design, Video Editing, Web Development (HTML and CSS only).

- Daily work of 1 to 2 hours and two meetings per week, in person and online.

- A supervising teacher, one video editing mentor, supporter students, and a guest speaker (digital marketing).

- The Debo Rise logo and the Telegram group are done.

- You have time to hold an info session and explain the program.

- Web final project idea: a responsive website for one business.

- Conversations with the graphic design contact have started.

### Still open (with a deadline for each)

| Open item | Why it matters | When |
| --- | --- | --- |
| Principal’s written approval and parent note | Protects you, the school, and the students. Nothing should be announced without it. | Tomorrow (Day -10) |
| Video final project and editing tool | Students need a clear target and a tool that works on their devices. | Tomorrow, with the video mentor |
| Graphic design mentor | Without a mentor, design students lack feedback. A backup plan is in Section 12. | Firm answer by Day -4 |
| Start date, Showcase date, and exam dates | The 6 weeks must avoid exams. | Tomorrow |
| Google Form and tracking Sheet | Needed to take applications and track results. | Day -9 |
| Certificate design and signatures | Decide who signs and what the school stamp or logo looks like. | Before Week 5 |
| Learning playlists and worksheets | Week 1 must be ready before Day 1. After that, always stay one week ahead. | Week 1 by Day -1 |
| Device and internet plan | Some students may have no laptop or weak internet. | Found out from the form on Day -4 |

### Key dates to fill in tomorrow

| Milestone | Date |
| --- | --- |
| Approval from the principal | [date] |
| Announcement and applications open | [date] |
| Info session and taster | [date] |
| Applications close | [date] |
| Selection and notifications | [date] |
| Day 1: Kickoff | [date] |
| End of Week 6 / Showcase Day | [date] |
| Final report to the principal | [date] |

# 3. Team and Roles

| Role | Responsibilities |
| --- | --- |
| Program lead (you) | Runs the program, teaches Web Development, posts announcements, reviews submissions, updates the tracker, and writes the final report. |
| Supervising teacher | Is a member of every Telegram group, approves the rules, helps with selection, follows up with students who struggle, and attends Showcase Day. |
| Video editing mentor | Confirms the video final project and tool, gives practice footage, and gives feedback on the video students’ work. |
| Graphic design mentor (to find) | Gives feedback on logos, posters, and brand kits, and judges the design projects. |
| Supporter students (2 or 3) | Take attendance, send reminders, help at Showcase Day (host, photos, tech), and check on quiet students in a friendly way. |
| Guest speaker (digital marketing) | One online session in Week 5 (30 to 45 minutes) on how to present and share your work online. |
| Principal | Gives approval, authorizes the certificate, attends Showcase Day, and can later introduce the program to the education office. |

Mentor time (suggested, confirm with each mentor) Ask each mentor for four touchpoints across the pilot: a live kickoff Q&A in Week 1, a review in Week 3 or 4 (live or written), a final project review in Week 5, and judging at Showcase Day in Week 6. Between these, they can answer questions in the group when they have time. Do not promise students more than the mentor has agreed to.

Protect your own workload You are leading the program, teaching Web Development, and preparing for Grade 12 exams. Ask one supporter student to run attendance and reminders. If you can, invite a developer friend to review the web students’ code once a week. Keep your own exam days free of program duties.

# 4. Approvals and Paperwork (to settle tomorrow)

| Document or approval | What it should contain |
| --- | --- |
| Principal’s written approval | Name of the program and dates, name of the supervising teacher, use of rooms and time, permission to issue a school-authorized certificate, and permission for Showcase Day. |
| Parent information and consent note | What the program is, the dates, daily time needed, that it is supervised, that groups are online on Telegram, permission for photos or videos of the student (for the Showcase and reports), a contact number, and a parent signature. |
| Group rules | The short rules in Appendix B, pinned in every Telegram group and signed or accepted by every student. |
| Room and schedule booking | A room for Meeting A each week, computer room slots for students without laptops, and the hall for Showcase Day. |
| Introduction letter (later) | A short letter from the principal you can use when you meet the education office after the pilot. |

# 5. Pre-Launch: Announce, Select, Onboard

Use about 10 days. If you must start sooner, compress the timeline, but never skip the approval, the parent note, or the group rules. Days with a minus sign are before the program starts. Day 1 is the Kickoff.

| Day | Action | Owner | Done |
| --- | --- | --- | --- |
| Day -10 (tomorrow) | Meet the principal: written approval, supervising teacher named, certificate authorization, rooms, and Showcase date. Prepare the parent note. Meet the video mentor: choose the final project and tool. Confirm start date and exam dates. | You, principal, video mentor | ☐ |
| Day -9 | Create the Google Form and tracking Sheet. Finish the poster in Debo Rise colors. Write the announcement. Ask the school to announce in assembly or classrooms. Get a firm yes or no from the graphic design contact. | You, supporters | ☐ |
| Day -8 | Launch: announce at school, put up posters, post in school Telegram groups, word of mouth. Applications open. | You, supporters, teacher | ☐ |
| Day -6 | Info session and taster (60 minutes, agenda below). Offer a second short session or a Telegram Q&A for students who missed it. | You, mentors | ☐ |
| Day -5 | Reminder posts and Q&A. Confirm the Showcase date with the principal. | Supporters | ☐ |
| Day -4 | Applications close. Undecided students confirm a field by a short poll. Go or no-go on Graphic Design (see backup plan in Section 12). | You | ☐ |
| Day -3 | Select students with the teacher (rubric below). Message accepted students and the waitlist. Send the parent note. | You, teacher | ☐ |
| Day -2 | Parent notes returned. Create Telegram groups, add accepted students, pin the rules, post the welcome message and the pre-survey link. | You, supporters | ☐ |
| Day -1 | Final check: room booked, Week 1 lessons and worksheets ready, attendance sheet ready, mentors reminded, supporters briefed. | You | ☐ |
| Day 1 | Kickoff (Meeting A, in person). | Everyone | ☐ |

## 5.1 Info Session and Taster (60 minutes)

This session also helps students who “just want to learn something” but do not know what. They see all three fields in action before they choose.

| Minutes | Part | Who |
| --- | --- | --- |
| 5 | Welcome and the problem: dreams without proof | You |
| 10 | What Debo Rise is: the method, 6 weeks, certificate, Showcase Day | You |
| 30 | Taster: three 10-minute mini-demos (Web, Design, Video). Show something students could make in 6 weeks. | You and mentors |
| 5 | The commitment and rules: 1 to 2 hours daily, 2 meetings a week, grades come first | You or teacher |
| 10 | Questions, and how to apply | You |

## 5.2 Application Form (Google Form)

- Full name, grade and section

- Telegram username and phone number

- Parent or guardian name and phone number

- First-choice field: Web Development, Graphic Design, Video Editing, or Not sure yet

- Second-choice field

- Why do you want to join? (2 or 3 sentences)

- Experience in any of these fields: none, a little, some

- Can you give 1 to 2 hours every day for 6 weeks? (yes, mostly, no)

- Can you attend two meetings a week, one in person and one online? (yes or no)

- What device do you have: phone, laptop, or both? Do you have internet at home: yes, limited, or no?

- Any exams or other commitments during the 6 weeks?

- I understand that grades come first and that parent permission is needed (checkbox)

## 5.3 Selection Rubric

| Step | Rule |
| --- | --- |
| Must have | Can attend both meetings each week, can give about 1 hour or more daily, and has parent permission. |
| Score 1 to 5 | The motivation answer shows real interest or a real wish to learn, even if the student is undecided. |
| Balance | About 8 to 10 students per field. Include some undecided students who have chosen a field after the taster. |
| Waitlist | Keep about 5 students. If someone drops out in Week 1, the next student joins. |
| Fairness | Beginners are welcome. Do not reject a student only for lacking a laptop; use the school computer room (see Section 12). |

## 5.4 Telegram Setup

| Space | Purpose | Who posts |
| --- | --- | --- |
| Debo Rise Announcements (channel) | Schedules, reminders, weekly summaries, deadlines. | Lead and teacher only |
| Debo Rise Community | General group for all students: wins, questions, motivation. | Everyone, with rules |
| Web Development group | Lessons, tasks, daily proof, #CallADebo requests. | Students, lead, teacher |
| Graphic Design group | Same, for design. | Students, mentor, teacher |
| Video Editing group | Same, for video. | Students, mentor, teacher |
| Admin group (private) | Coordination between lead, supporters, and teacher. | Admins only |

The supervising teacher is in every group. Mentors answer only inside the groups. Rules are pinned (Appendix B).

# 6. How the Six Weeks Work

## 6.1 Learn, Think, Build, Solve, Teach

Each week has a main focus, but learning never stops. Every week brings new lessons so students always have the skills for the next step.

| Week | Phase | Main question | Result |
| --- | --- | --- | --- |
| 1 | Learn | What is this skill and how does it work? | Basics and a first small task. |
| 2 | Think | Who is this for, and what problem am I solving? | Choose a real client. Write a brief and plan. Learn more core skills. |
| 3 and 4 | Build | Can I make it real? | Week 3: first draft of the project. Week 4: full working draft. |
| 5 | Solve | Does it work for a real person? | Test with the client, collect feedback, and improve. Final project. |
| 6 | Teach | Can I explain and share what I learned? | Teach-back, presentation, and Showcase Day. |

## 6.2 The Weekly Rhythm

Days are suggestions (for example, Meeting A on Monday and Meeting B on Thursday). Adjust to your school timetable, then keep it fixed for all 6 weeks.

| Day | What happens |
| --- | --- |
| Day 1 | Meeting A, in person (60 min). Weekly goal, discussion question, demo, first task. |
| Days 2 and 3 | Daily work (1 to 2 hours). Post proof in the group. |
| Day 4 | Meeting B, online (45 min). Progress sharing and problem solving. |
| Day 5 | Daily work (1 to 2 hours). Post proof. |
| Day 6 | Finish and submit the weekly deliverable (about 1 hour). |
| Day 7 | Rest day for students. The lead and supporters review submissions, update the tracker, give feedback, and post a short weekly summary. |

## 6.3 The Daily Routine (1 to 2 hours)

| Time | Step | What to do |
| --- | --- | --- |
| 5 min | Read | Read today’s task in the field group. |
| 30 to 45 min | Learn | Watch the lesson segment (links and timestamps are given) and take notes. |
| 30 to 60 min | Practice | Do the day’s task. Make something, even if it is small. |
| 5 to 10 min | Post proof | Post a screenshot, photo, or short note with the day number (for example #Day3). |

Stuck for 20 minutes? Post #CallADebo with a screenshot and a clear question. Like a debo in our villages, classmates and mentors gather to help one person finish their work. Helping others also counts as practice for the Teach phase.

## 6.4 Meeting Templates

| Meeting | Agenda |
| --- | --- |
| Meeting A (in person, 60 min) | 5 min: welcome and wins from last week. 10 min: Think discussion (the weekly question). 30 min: lesson demo by mentor or lead, then practice in field groups. 10 min: weekly goal and tasks. 5 min: attendance and a quick photo (with permission). |
| Meeting B (online, 45 min) | 5 min: check-in. 10 min: two or three students show their work. 20 min: #CallADebo problem solving. 5 min: plan for the next days. 5 min: attendance and wrap-up. |

# 7. Week-by-Week Lesson Plan

Deliverables are due on Day 6. All lessons are for complete beginners. Links to the chosen lessons are added by you (see Section 8).

## Week 1: Learn

Goal: Understand the basics of the skill and finish a first small task.

Think question for Meeting A: What do I want to be able to do in 6 weeks, and what could stop me?

Mentor focus: Live kickoff Q&A. The mentor shows a finished example and explains how they started.

Day 1 Kickoff (60 min, in person) 15 min whole group: welcome, the Debo story, rules. 5 min: pre-survey. 30 min field groups: meet the mentor, set up tools, first lesson. 10 min: weekly goal and first task.

| Day | Web Development | Graphic Design | Video Editing |
| --- | --- | --- | --- |
| Day 1 · Meeting A (in person) | How websites work (browser, HTML, CSS). Install VS Code. Create your first page and folder. | What graphic design is. Set up Canva. Canvas sizes, interface, and exporting. | What editing does. Set up the tool chosen with the mentor. Import clips, timeline, export settings. |
| Day 2 | Text elements: headings, paragraphs, links. Page skeleton (doctype, head, body). | Layout and alignment: margins, spacing, grid. Visual hierarchy (what is read first). | Cutting and trimming: keep the best moments and remove the rest. |
| Day 3 | Images, lists, file paths, and alt text. | Contrast and color basics: color wheel, light and dark, readable text. | Audio basics: music, voice, volume levels, fades. |
| Day 4 · Meeting B (online) | Semantic structure: header, nav, main, section, footer. Fix bugs together. | Typography basics: use at most 2 fonts; size and weight. Review Day 2 and 3 work. | Text titles and simple transitions (less is more). Review practice cuts. |
| Day 5 | Build an “About Me” page using everything learned. | Practice: recreate a simple poster from a reference by eye. | Practice edits with the mentor’s practice footage (30 to 45 seconds). |
| Day 6 | Finish, check, and submit the weekly deliverable (about 1 hour). Day 7 is a rest day. |  |  |
| Deliverable | “About Me” HTML page (screenshot and code) | Recreated poster and your improved version | 30 to 45 second practice edit |

## Week 2: Think

Goal: Choose a real client, understand their needs, and plan the final project.

Think question for Meeting A: What makes something good for a real person, not just nice to look at?

Mentor focus: Written feedback on each student’s brief and plan.

| Day | Web Development | Graphic Design | Video Editing |
| --- | --- | --- | --- |
| Day 1 · Meeting A (in person) | Intro to CSS: link a stylesheet, selectors, colors. Group task: analyze 3 business websites. | Design solves a problem: audience, message, feeling. Group task: compare 3 good and 3 weak posters. | Storytelling: hook, middle, end. Group task: analyze 3 short videos and what keeps attention. |
| Day 2 | CSS typography (font-family, size, line-height) and colors (hex codes). | Color for brands: build 3 palettes for a sample brand. | Shot types (wide, medium, close-up) and phone camera basics: steady shots, light, vertical or horizontal. |
| Day 3 | Box model: margin, padding, border. Style your About Me page. | Fonts for brands: choose font pairs that match a mood. | Clean audio and light with a phone. |
| Day 4 · Meeting B (online) | Choose the business for your website. Write 5 questions to ask the owner. | Choose your client (school club or local business). Write 5 interview questions. | Choose the subject of your video (club, event, or business). Write 5 questions for the client. |
| Day 5 | Meet the business owner. Write a 1-page brief: customers, sections needed, content. | Interview the client. Write a 1-page brief: goal, audience, style, needs. | Interview the client. Write a short concept and script outline. |
| Day 6 | Finish, check, and submit the weekly deliverable (about 1 hour). Day 7 is a rest day. |  |  |
| Deliverable | Business brief, paper wireframe (mobile and desktop), and content list | Client brief and moodboard (images, colors, fonts) | Concept, storyboard, and shot list |

## Week 3: Build (part 1)

Goal: Start creating the real project.

Think question for Meeting A: What is the hardest part so far, and how will I solve it?

Mentor focus: First build review (live or written).

| Day | Web Development | Graphic Design | Video Editing |
| --- | --- | --- | --- |
| Day 1 · Meeting A (in person) | Flexbox basics: rows, columns, alignment. | Logo basics: wordmark, symbol, combination. A good logo is simple, memorable, and works small. | Filming plan: schedule, locations, permission, and consent from anyone on camera. |
| Day 2 | Build the header and navigation bar. | Sketch 10 logo ideas on paper. | Film with permission. Organize files in clearly named folders. |
| Day 3 | Build the hero section: image, headline, button, hover effect. | Turn the best 3 ideas into digital logos using your own shapes and text. | Film more footage and record audio. Check quality on the day. |
| Day 4 · Meeting B (online) | Cards with Flexbox for services or products. Code review together. | Group feedback: choose the strongest logo and list improvements. | Rough-cut workshop: build the story on the timeline. |
| Day 5 | Build About and Contact sections and the footer. | Finalize the logo: color and black-and-white versions, spacing, PNG export. | Continue the rough cut. Add music and basic titles. |
| Day 6 | Finish, check, and submit the weekly deliverable (about 1 hour). Day 7 is a rest day. |  |  |
| Deliverable | Homepage draft (desktop view) | 3 logo concepts and 1 final logo | All footage and a rough cut |

## Week 4: Build (part 2)

Goal: Complete a full working draft of the project.

Think question for Meeting A: What would a real user complain about in my work?

Mentor focus: Live review of full drafts.

| Day | Web Development | Graphic Design | Video Editing |
| --- | --- | --- | --- |
| Day 1 · Meeting A (in person) | Responsive design: viewport meta tag, flexible widths, mobile-first. Test with browser developer tools. | Brand consistency: logo, colors, and fonts as a mini brand kit. Poster principles: one message, one focal point. | Pacing and rhythm: tighten cuts. Use B-roll to cover weak shots. |
| Day 2 | Media queries: adapt the navigation and layout for phones. | Sketch the poster layout, then build version 1 in Canva. | Titles, captions, and a consistent text style. |
| Day 3 | Responsive images, spacing, and readable text on small screens. | Poster version 1: imagery, text hierarchy, brand colors. | Sound mixing: clear voice, music lower than speech. |
| Day 4 · Meeting B (online) | Peer and mentor code review. Write a list of fixes. | Peer critique with a checklist (hierarchy, contrast, consistency). Write a fix list. | Mentor feedback on the rough cut. |
| Day 5 | Complete the remaining sections or pages and link the navigation. | Create a social media post in the same brand style. | Color basics: brightness, contrast, a consistent look. Build fine cut version 1. |
| Day 6 | Finish, check, and submit the weekly deliverable (about 1 hour). Day 7 is a rest day. |  |  |
| Deliverable | Full responsive website draft | Poster and social media post | Fine cut version 1 (full video) |

## Week 5: Solve

Goal: Test the project with a real person and improve it.

Think question for Meeting A: What did the real person say that surprised me?

Mentor focus: Final project review against the scoring checklist (Section 9).

| Day | Web Development | Graphic Design | Video Editing |
| --- | --- | --- | --- |
| Day 1 · Meeting A (in person) | Testing: phone and different browsers. Checklist: links, images, readability, contrast. | Presenting to a client: explain why, not only what. Test readability from a distance and on a phone. | Test screening: watch together and note where attention drops. |
| Day 2 | Show the draft to the business owner. Collect feedback with 5 simple questions. | Present the brand kit to the client. Collect feedback with 5 simple questions. | Show the video to the client or an audience. Collect feedback with 5 simple questions. |
| Day 3 | Fix issues from feedback. Accessibility basics: alt text, color contrast, readable fonts. | Revise using feedback. Export correct formats (PNG, PDF, print-ready). | Revise. Add subtitles. Check audio on phone speakers. |
| Day 4 · Meeting B (online) | Guest speaker (digital marketing): how to present and share your work online. Then Q&A and #CallADebo. |  |  |
| Day 5 | Final polish. Optional: publish the site for free (for example GitHub Pages or Netlify). Take screenshots. | Make a 1-page brand guide: logo, colors, fonts, do’s and don’ts. Optional: print test of the poster. | Export for platforms: vertical 9:16 and horizontal 16:9. Make a thumbnail. |
| Day 6 | Finish, check, and submit the weekly deliverable (about 1 hour). Day 7 is a rest day. |  |  |
| Deliverable | Final website and a feedback record (what they said, what you changed) | Final brand kit and a feedback record | Final video and a feedback record |

## Week 6: Teach

Goal: Explain and share what you learned, and present your work.

Think question for Meeting A: What did I learn that I can teach someone else?

Mentor focus: Judging at Showcase Day.

| Day | Web Development | Graphic Design | Video Editing |
| --- | --- | --- | --- |
| Day 1 · Meeting A (in person) | Teach-back practice: teach one concept in 5 minutes to your field group. Idea: how a responsive navbar works. | Teach-back practice: teach one rule in 5 minutes. Idea: how hierarchy guides the eye. | Teach-back practice: teach one technique in 5 minutes. Idea: how to open with a strong hook. |
| Day 2 | Build your presentation (3 to 5 minutes): the client and problem, your process, the result, the feedback you received, and what you learned. Web students prepare a live demo. Design students prepare before and after slides. Video students prepare the final video and a one-minute story. |  |  |
| Day 3 | Rehearse twice. Make a backup of your project (screen recording, exported images, or the final video file) in case of technology problems. |  |  |
| Day 4 · Meeting B (online) | Rehearsal in front of your mentor. Final checks: files, links, device, and what to bring to Showcase Day. |  |  |
| Day 5 | SHOWCASE DAY (in person). See Section 10 for the program. |  |  |
| Day 6 | Reflection: complete the post-survey, write a short testimonial, thank your mentors. Lead collects the final data for the report. |  |  |
| Deliverable | Presentation, teach-back, and all final project files saved in the shared folder. |  |  |

# 8. Learning Content System

Your mentors guide the process, and curated online lessons carry the daily learning. Curate, do not copy: link to the original videos and add your own worksheets.

## 8.1 The Lesson Card (one for every lesson)

| Part | What it contains |
| --- | --- |
| Goal | One sentence: “By the end you can …” |
| Watch | Link to the chosen video with exact start and end times (about 10 to 20 minutes). |
| Do | The practice task (30 to 60 minutes). |
| Check yourself | 3 short questions. |
| Proof | What to post in the group (screenshot, photo, or short note). |

### Example: Web Development, Week 1, Day 2

| Part | Content |
| --- | --- |
| Goal | By the end you can write headings, paragraphs, and links in HTML. |
| Watch | [Link to a beginner HTML text lesson, with timestamps] |
| Do | Create index.html with one main heading, two sub-headings, three paragraphs, and two links. |
| Check yourself | What is the difference between a main heading and a sub-heading? What does the href attribute do? Why does every page need a title? |
| Proof | A screenshot of your page in the browser and of your code. |

## 8.2 How to Choose and Prepare Videos

- For each lesson, find 2 or 3 candidate videos and watch them fully before choosing.

- Choose videos that are clear, accurate, beginner-friendly, and recent. Tool interfaces change, so be careful with videos older than about 3 years.

- Write the exact timestamps to watch. Prefer short segments.

- Check whether good Amharic-language lessons exist for the same topic. Mix them in if they are good.

- Ask your mentor to review the sequence for each field.

- Share links only. Do not download, trim, and re-upload other creators’ videos.

- Write the worksheet yourself so the lesson works even if a video is removed. Keep a backup video for each lesson.

- Check every link 2 days before the week starts.

## 8.3 Sources to Check First

These are starting points only. I cannot check what is currently posted, so preview every video before you use it.

| Field | Where to look |
| --- | --- |
| Web Development | freeCodeCamp (HTML and CSS courses), Kevin Powell (CSS and responsive design), SuperSimpleDev (beginner HTML and CSS), and MDN Web Docs for written reference. |
| Graphic Design | Canva Design School (Canva’s own tutorials), Satori Graphics (design basics), plus your design mentor’s recommendations. |
| Video Editing | The official tutorials of the tool you choose with your mentor, plus your video mentor’s recommendations. |

## 8.4 Tools

| Field | Tool | Notes |
| --- | --- | --- |
| Web Development | VS Code and a browser (Chrome or Edge) | Free. Works offline. Needs a laptop or a school computer. |
| Graphic Design | Canva (free) | Works on phone and laptop. Needs internet. Check Canva’s license terms before using a logo commercially. |
| Video Editing | To be decided with the mentor (for example CapCut, or DaVinci Resolve on a strong computer) | Choose a tool that works on the students’ devices. |
| All fields | Telegram, Google Drive shared folder, Google Sheet tracker, Google Form | One folder per field with one sub-folder per student for project files. |

# 9. Final Projects, Scoring, and Certificate

## 9.1 What Counts as “Done”

| Field | Final project | Minimum to count as finished |
| --- | --- | --- |
| Web Development | A responsive website for one real business | At least a homepage with header and navigation, hero, services or products, about, contact, and footer. Works on phone and desktop. Clean HTML structure and CSS only. Tested on a phone. Feedback record. |
| Graphic Design | A mini brand kit for a real client | Final logo (color and black-and-white), color palette and 2 fonts, 1 poster, 1 social media post, 1-page brand guide. Feedback record. |
| Video Editing | A short promo video (to be confirmed tomorrow) | 60 to 90 seconds, clear story, clean cuts, readable text or captions, balanced audio, correct export format. Feedback record. |

## 9.2 Scoring Checklist (100 points)

| Category | Points | What mentors look for |
| --- | --- | --- |
| Project completed | 30 | All minimum requirements are met and the project is submitted on time. |
| Quality of work | 30 | Web: works on phone, clean structure. Design: hierarchy and consistency. Video: pacing and sound. |
| Real problem and feedback | 20 | Worked with a real client, collected feedback, and showed what changed. |
| Presentation and teach-back | 10 | Clear, honest, and well prepared. |
| Participation | 10 | Attendance, daily proof, and helping others (#CallADebo). |

A score of 60 or more is a pass. Mentors and the supervising teacher agree on scores together.

## 9.3 Certificate Rules

| Requirement | Standard |
| --- | --- |
| Meetings | Attend at least 9 of the 12 meetings (75%) and the Showcase Day. |
| Daily proof | Post proof at least 4 days each week (about 24 posts). At least 20 posts are needed. |
| Project | Finish and submit the final project with a score of 60 or more. |
| Presentation | Present at Showcase Day (stage or exhibition station). |
| Grace period | Students who are close but not finished get 7 extra days after Showcase Day to complete the project. |

What the certificate shows: the student’s name, field, project title, “Completed the Debo Rise 6-Week Pilot”, the dates, the signatures of the school director and the program lead, the school stamp, and a certificate number (for example DR-P1-001). The certificate number lets anyone check it later. The school’s authorization must be approved by the principal first.

# 10. Showcase Day (2 hours)

| Minutes | Part |
| --- | --- |
| 10 | Opening: welcome by the principal and you. |
| 30 | Stage presentations: 2 students per field (6 in total), 4 minutes each. Chosen by the mentors using the scoring checklist. |
| 30 | Exhibition: every student has a station (laptop or printed work) and explains their project in 2 minutes to visitors. |
| 10 | Comments from guests and mentors. |
| 25 | Certificate ceremony. |
| 5 | Closing and thanks. |
| 10 | Group photo and mentor thank-you. |

### Roles

Host (supporter student), timekeeper, photographer (only students with consent), tech lead (projector, laptops, power), certificate handler, guest welcome, and feedback cards for the audience.

### Checklist

- Hall booked and invitations sent 7 days before (principal, teachers, parents, mentors, and optionally education office staff).

- Projector, screen, extension cords, charged laptops, and tables for the exhibition.

- Offline copies of every project on a laptop or USB drive, plus a phone backup.

- Certificates printed, signed, and stamped. Name tags. Printed programs.

- Photo consent confirmed. Group photo planned.

# 11. Tracking, Surveys, and the Final Report

| What | How | When |
| --- | --- | --- |
| Applications and selection | Google Form and Sheet | Pre-launch |
| Attendance (12 meetings) | Attendance sheet, kept by a supporter | Every meeting |
| Daily proof posts | Count from the groups, entered in the Sheet | Weekly (Day 7) |
| Weekly deliverables | Submission folder and a checklist | Weekly (Day 7) |
| Confidence survey (1 to 5) | Same short questions before and after | Day 1 and Day 6 of Week 6 |
| Final project score | Scoring checklist from mentors | Week 5 and Week 6 |
| Testimonials | 3 questions to students, mentors, and the teacher | Week 6 |

### Survey questions (rate each 1 to 5)

- I can do the main skill of my field on my own.

- I can finish a real project.

- I know my next step after this program.

- I feel confident presenting my work.

In the post-survey add: What was most useful? What should we change? How likely are you to recommend it (0 to 10)?

### Early warning

If a student misses 2 meetings or posts no proof for 5 days, a supporter or the teacher follows up in a friendly way (in the group or in person at school). Mentors do not message students privately.

### Final report to the principal (1 to 2 pages)

Number who applied, joined, and finished. Attendance rate. Photos of the best projects. Change in confidence scores. Testimonials. Lessons learned. Recommendations for the second cohort. This report is also the proof you will show the education office.

# 12. Risks and Backup Plans

| Risk | Backup plan |
| --- | --- |
| Fewer than 20 applicants | Extend the deadline by 2 days, invite students personally through teachers, and start with a smaller group. A pilot with 15 students is still a valid test. |
| Too many applicants | Use the waitlist and plan a second cohort. |
| Students drop out | Friendly follow-up. Fill early gaps from the waitlist in Week 1. Allow rejoining in Week 2 only. |
| No graphic design mentor by Day -4 | Option A: run design with curated lessons and peer review, plus feedback sessions from your design contact in Weeks 2, 4, and 5. Option B: run only two fields now and offer design in the second cohort. Tell students before they choose a field. |
| A mentor is unavailable | Give written feedback in the group, play a recorded session, or the lead covers the session. |
| Your workload | Supporters handle attendance and reminders. A developer friend reviews code weekly. Use the checklist for feedback. Protect your exam days. |
| No laptop or weak internet | Use school computer room slots after class. Choose phone-friendly tasks where possible. VS Code works offline. |
| Power or internet cuts | Allow a 1-day grace on deadlines and post notes in Telegram so they can be read later. |
| Exams or school events clash | Choose dates now. If needed, pause for at most one week. |
| Broken or removed video links | Check links 2 days before each week, keep a backup video, and keep worksheets independent of the video. |
| Online safety or conduct problem | Teacher in every group, pinned rules, mentors only in groups, remove members who break the rules, and contact parents when needed. |
| Copyright concerns | Link, do not copy. Students make original work and use free or permitted images, music, and fonts. Credit sources. |
| Low discussion in Think sessions | Start with small-group questions and let supporters seed the discussion. Give a weekly shout-out for the best help or best progress. |
| Technology fails on Showcase Day | Offline copies, printed work, and a phone backup. |

# 13. Next Actions

### Tomorrow (Day -10)

- Meet the principal: written approval, teacher named, certificate authorization, rooms, Showcase date.

- Meet the video mentor: choose the final video project and the editing tool; get practice footage.

- Get a firm answer from the graphic design contact (or a date for it).

- Fix the start date and make sure the 6 weeks avoid exams.

- Draft the parent note.

### Before announcing (Days -9 to -8)

- Build the Google Form and Sheet.

- Finish the poster and the announcement text.

- Brief the supporter students.

### Before Day 1

- Select students, send the parent note, create the groups.

- Prepare Week 1 lesson cards for all three fields.

- Book the room and check the Meeting B online link.

# Appendix A: Announcement Text

Will prepare

# Appendix B: Group Rules (will be pin in every group)

- Be respectful. No bullying, insults, or harassment.

- Do not share personal information such as phone numbers, addresses, or photos of others without permission.

- Stay on topic. No harmful, adult, or off-topic content.

- Make original work. Credit your sources and do not copy others’ work as your own.

- Post your proof of work at least 4 days a week.

- Stuck? Use #CallADebo with a screenshot and a clear question, and help others when you can.

- Mentors and teachers communicate only inside the groups, not in private chats.

- Photos or videos of people are shared only with their permission.

- Admins and the teacher can remove members who break the rules.

- Grades come first. Tell us if you need a break.